## Sheet1
| number of parts | Description | input | output | Input Dependency | Input dependencies Contact | Output Dependency | Output dependencies Contact | Pitfalls | SOP
Step 1 | 11 | Generates master list from Services websites | Services Website | Species list that includes species from both Services | Formatting of website - changes to website will mean updates to tool | Jen | Agreement from Services; feedback from chemical teams | Colleen/ Chemical Team Keith Paul FWS; Thom Hooper NMFS | Drives spatial data collection change after lock will require all overlap to updated for species groups with changes | No - B/C of NMFS site; FWS is user prompts
Step 2 | 10 | Sets a standard file name and standardized range files received from Services to a single part polygons, one file per species, common geographic projection, and attribute information | New or updated species location file | standardize file | Receiving new/updated range file from service | Keith Paul - FWS; Thom Hooper -NMFS | Access to current spatial library | Jen | All files must be received before locking spatial libraries or all overlap must be updated for species group | Yes
Step 3 | 9 | Moves new/updated GIS files to spatial libraries; archives old files; generates HUC12 files for aquatic species; runs geo repair and generalization; Check for missing species files against Master Species needed for risk assessment | standardize new or updated species location file | update spatial libraries | complete standardization - can happen on a rolling basis | Jen | Can't generate new composite files for overlap until spatial library are locked | Jen | New files must be received and process before locking species spatial libraries | Yes
Step 4 | 20 | Generates species overlap composite files; supporting tables for overlap; standardized use layers for overlap | Use layers; species spatial libraries | Unioned species composites as rasters (ZoneID) by species group and region; Unioned species usage composites as rasters (InterID) by species group and region; Standardized use layer library ; supporting tables needed for overlap | Use layers from Steve; composite files from Jen | Steve/Jen | Use layers must meet risk assessment modelling assumptions; All species location files and species information needed for risk assessment account for; if new information need to add steps will need to be repeated | Colleen/Team Leads | Projection matters, species composites and use layer in region must match and can't change or tables will be empty; Output from this step used as inputs in following steps, changes will mean repeating steps | Yes
Step 5 | 10 | Runs overlap | Unioned species composite (zoneid); unioned usage/species composites (interid) | raw overlap tables by use | species composite; use layer library | Chemical teams for generate question; Colleen tools | Raw output must have all data needed for parent tables and chemicals tables need for risk assessment tools | Jen | Additional species information, changes to use layer, or assumptions for parent tables will mean repeating Step 4 and 5 as well as any down stream Step that have been worked on | Yes but needs to be updated for usage
Step 6 | 5 (species) 7 (HUC12s) | Tabulates species runs ; parent tables need for risk assessment tools and chemical usage tables | Species and usage composites; Use layer library; chemical use layer list ; unioned species composite as lookup | parent tables used in risk assessment tools or used to generated species overlap tables using usage information | agreement from chemical team on uses that need included and application methods for uses captured in chemical use layer list | Chemical team lead | Formatting must meet criteria for MagTool/ Post processor/ other risk assessment tools ; column headers for all output tables are set by species master list or chemical use layer list | Colleen, Chuck , chemical team | Changes to species files, use layers, or species information will require re-doing previous steps; changes to tables that set formatting could impact risk assessment tools; uses for chemical must be included in composite with the appropriate buffers restriction if need - THIS CANNOT BE ACCOUNTED FOR IN OVERLAP OUTPUT WITHOUT AN UPDATE TO THE USE LAYERS | Yes need to be updated to account for more recent changes
Step 7 | 14 | Standardize SUUM; applies usage to overlap tools; output tables to risk assessment | usage table; use layer master list | tables for risk assessment tool and overlap sections of the BE; master PCT tables by chemical | SUUM from BEAD - must meet formatting criteria combined with additional crop information from NASS ; crosswalks of all sources of data to the General classes ; formatting of this table must meet the needs of the tool | BEAD SUUM data, Colleen/Chuck -input usage table that combined with all necessary information | Formatting must meet criteria for MagTool and other risk assessment tools; additional information may be difficult add in on the backend | Colleen | Changes to crops will require adjustments to crosswalks and may cause use layers to be updated; Changes to usage input table needs to be complete and in the correct format before output tables can be finalized; all steps down stream of impacts will need to re-done; changes to scale of usage i.e. from state to county will require some re-development and to incorporate usage not bound by political would be complete re-development | Needs to finalized based on recent updates to usage